## Sheet1
# | Program/Project | Element, page numbers | Potential Partners | Time Frame | 2024 Status + Comments
1. | Extension of Santa Fe County Water Lines in Upper La Cienega and La Cieneguilla | Water Service Priority Area | LC/LC Community Organization LCVA, County, NMED, Federal Government | Medium | To do
2 | PFAS and other emerging contaminants remediation planning | Water | LCVA, County, City, NMED, Federal Government | Medium | New
3 | Fuel Mitigation & Fire/Flood Response Program | Public Safety | County Fire, LCVA, Acequia Associations, BLM, USFS | Shortmedium | New
4 | New Joint City/County Wastewater Treatment Plant | Water | LCVA, County, City, NMED, Federal Government | Medium-Long | New + communtiy advocacy for a joint City/County Water Strategy
5 | Develop Incentive Zoning, Land Use and Development Standards in support of the preservation or expansion of contiguous agricultural lands and acequia systems. | Traditional Irrigated Agricultural Land Preservation | Acequia Associations, Property Owners, LC/LC Community Organization LCVA, County | Shortmedium | Some incentives were enacted (i.e. TDR program), but more support for preservation and expansion can be done.
6 | Analyze supplemental water to use for irrigation | Existing Conditions, Goals and Strategies Water Resources | Acequia Associations, State Penitentary, National Guard, SF Wastewater, Treatment Plan, Property Owners, LC/LC Community Organization LCVA, County | Short | To do
7 | Wastewater Feasibility Study | Existing Conditions, Goals and Strategies Water Resources | County Public Works, NMED, EPA, USDA | Shortmedium | The Spring Restoration Study will look into wastewater + ask Robert Romero about the Wastewater Study
8 | Implement the Transportation Safety Study Community Pedestrian and Equestrian Circulation Study | Transportation Community Parks, Open Space & Trails | LC/LC Community Organization LCVA, County Open Space | Shortmedium | New + the upcoming Transportation Safety Study will examine pedestrain and equestrain to a certain extent.
9 | La Bajada Ranch Conceptual Plan and Outreach | Open Space | County, LCVA | Short | New
10 | Agricultural Lands Directory | Agriculture | Acequia Associations, LC/LC Community Organization LCVA, County, USDA Farm & Ranch | Medium | To do
11 | Multipurpose, Multigenerational Community Center , Conduct a needs assessment | Community Facilities | LC/LC Community Organization LCVA, County, State Land Office | Shortmedium | To do
12 | Monitor water rights retirement schedules to ensure that compliance with said schedules are enforced for all water rights derived from the Community Planning Area. | Existing Conditions | Acequia Associations, LC/LC Community Organization LCVA | Short | ?
13 | Develop accurate population estimates for the La Cienega and La Cieneguilla Community Planning Area. These population figures will be used in conjunction with a water budget for the planning area to determine potential population impacts on local water resources and the development of realistic water availability estimates to guide future land use decisions. This study should be completed no more than 3 years from the date that the Plan is adopted | Existing Conditions | Acequia Associations, LC/LC Community Organization LCVA, County Planning, NM OSE | Short | County Planning Staff may be able to complete this as an internal study and may be able to remove this as a Implementation Matrix item.